## Sheet1
Sprint	Epic	Task	Assignee	Estimated time	Burndown chart link
1	Authentication	Sign Up	Lê Trường Thanh	3 h	https://agile-group2.atlassian.net/secure/RapidBoard.jspa?rapidView=2&projectKey=CSO&view=reporting&chart=burndownChart&sprint=3
		Register Function	Phan Huỳnh Văn Ngọc	3 h
		Design Login Page	Lê Quang Huy	4 h
		Login Function	Lê Trường Thanh	3 h
		Logout Function	Lê Trường Thanh	3 h
	Show List Product Of Store	Show List Product	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h
		Show List Product UI	Lê Quang Huy	2 h
2	Manage Product	Manage Products	Lê Trường Thanh	5 h	https://agile-group2.atlassian.net/secure/RapidBoard.jspa?rapidView=2&projectKey=CSO&view=reporting&chart=burndownChart&sprint=13
		Create Product	Lê Trường Thanh	3 h
		Read Product	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	3 h
		Update Product	Lê Trường Thanh	3 h
		Delete Product	Phan Huỳnh Văn Ngọc	2 h
		Get Product List	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	5 h
		Product List UI	Lê Quang Huy	4 h
		Product UI	Lê Quang Huy	4 h
	User information, Order's state and history.	Design UserInfor-page(FE)	Nguyễn Thái Sang	4 h
		Function see state of the order	Lê Trường Thanh	2 h
		Manage state of the order	Lê Trường Thanh	2 h
3	Manage Order	Manage order history	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h	https://agile-group2.atlassian.net/secure/RapidBoard.jspa?rapidView=2&projectKey=CSO&view=reporting&chart=burndownChart&sprint=14
		Function see full purchase history by day	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h
		Function see full purchase history by week	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h
		Function see full purchase history by month	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h
		Function see full purchase history by year	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h
		Cancel and change Order	Lê Trường Thanh	2 h
		Function cancel order	Lê Trường Thanh	2 h
		Function change order	Lê Trường Thanh	2 h
		Design Manage Order History UI	Lê Quang Huy	4 h
	Manage User	Get UserInfor UI	Lê Quang Huy	2 h	https://agile-group2.atlassian.net/secure/RapidBoard.jspa?rapidView=2&projectKey=CSO&view=reporting&chart=burndownChart&sprint=15
		Design Register-page UI	Lê Quang Huy	4 h
		Manage User	Lê Trường Thanh	2 h
		Get user information list	Lê Trường Thanh	2 h
		Get purchase history list	Lê Trường Thanh	2 h
		Design Manage User UI	Lê Quang Huy	2 h
	Cart	Cart UI	Lê Quang Huy	4 h
		Cart	Lê Trường Thanh	2 h
		Add To Cart	Lê Trường Thanh	2 h
		Update Cart	Lê Trường Thanh	2 h
		Delete from Cart	Lê Trường Thanh	2 h
4	CheckOut	Shipping Method	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	4 h
		Payment Method	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h
		Checkout UI	Lê Quang Huy	1 d
		External Payment UI	Lê Quang Huy	4 h
		Pickup method	Lê Trường Thanh	1 h
		Delivery method	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h
		Payment Direct	Lê Trường Thanh	2 h
		Payment by Paypal	Phan Huỳnh Văn Ngọc	3 d
		Analyze and Graph	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	6 h
		Send Email system	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h
		Test out system	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	2 h
		Create demo data	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	6 h
Extra	Document	Report writing	Phan Minh Tâm + Nguyễn Hoàng Kỳ Châu	None
			Lê Trường Thanh
			Phan Huỳnh Văn Ngọc
	Story and tasks deploy		Lê Quang Huy	None
	Extra tasks deploy		Nguyễn Hoàng Kỳ Châu	None